## Read Me
Library Management System: Test Plan and Tracker
Linked to Project Brief v1.0 (business rules BR-1 to BR-12, FR-1 to FR-10).
How to use this workbook
1. Work through 'Test Cases' feature by feature, right after each feature is built. Do not move on until the High priority cases pass.
2. Fill only the light-yellow columns: Actual result, Status, Tested by, Date, Notes. Everything else is fixed.
3. Status values: Not run, Pass, Fail, Blocked. The Summary sheet updates automatically.
4. When a case fails, paste the exact steps, expected and actual result into the AI chat as a bug report. Re-test, then re-run earlier High priority cases to catch regressions.
Example of a filled row (for format only)
Case: Block issue for a member with an unpaid fine. Actual result: Blocked with message 'Member has an unpaid fine'. Status: Pass. Tested by: Soham. Date: 2026-11-02.
Test data and setup tips
Use the seed data from the brief: 1 librarian, 2 students, about 30 books, 10 members, overdue transactions, one Unpaid and one Paid fine, one Inactive member, one book with 0 copies.
To test late returns without waiting, use the seeded overdue transactions, or for testing only edit a test transaction's issue and due dates in Supabase so it is N days overdue. Never do this to demo data you need.
Keep the demo data fictional. Do not use real classmates' details.
Test security cases (RLS) as a real student login, not just by hiding buttons.
Offline tests need the deployed HTTPS site. The AI Studio preview may not support service workers.
Assumption: priorities are my suggestion (High = core rule or security, Medium = important behaviour, Low = optional or design-level). Adjust to your marking scheme.
Sheets
Summary: pass/fail counts per feature.
Acceptance Criteria: plain-English statements per feature (paste the relevant ones into each build prompt).
Test Cases: the full checklist with steps, expected results and tracking columns.

## Summary
Test Progress Summary
Feature | Total | Pass | Fail | Blocked | Not run | Pass %
Login & Access Control | 14 | 0 | 0 | 0 | 14 | 0%
Catalogue Management | 12 | 0 | 0 | 0 | 12 | 0%
Member Management | 8 | 0 | 0 | 0 | 8 | 0%
Search & Availability | 12 | 0 | 0 | 0 | 12 | 0%
Issue Book | 18 | 0 | 0 | 0 | 18 | 0%
Return Book & Fines | 11 | 0 | 0 | 0 | 11 | 0%
Fine Payment | 7 | 0 | 0 | 0 | 7 | 0%
Student View | 6 | 0 | 0 | 0 | 6 | 0%
Slips & Printing | 4 | 0 | 0 | 0 | 4 | 0%
Offline Mode (PWA) | 7 | 0 | 0 | 0 | 7 | 0%
Non-Functional | 12 | 0 | 0 | 0 | 12 | 0%
Data Integrity & Dates | 7 | 0 | 0 | 0 | 7 | 0%
Total | 118 | 0 | 0 | 0 | 118 | 0%
High priority cases not yet passed: | 63

## Acceptance Criteria
ID | Feature | Linked requirement | Acceptance criterion
AC-AUTH-01 | Login & Access Control | FR-10 | Only users with valid credentials can access the app, and every dashboard page requires login.
AC-AUTH-02 | Login & Access Control | NFR-2 | Passwords are stored only as hashes, never as plain text.
AC-AUTH-03 | Login & Access Control | FR-10 | A student can sign up only with an email the librarian has already registered, and is linked to that member record.
AC-AUTH-04 | Login & Access Control | FR-10 / RLS | Students can never perform librarian actions or read other members' data, even by calling the database directly.
AC-CAT-01 | Catalogue Management | FR-1 | Librarian can add, edit and delete books, authors and categories. ISBN and category names must be unique.
AC-CAT-02 | Catalogue Management | FR-1 / BR-5 | A new book starts with available copies equal to total copies.
AC-CAT-03 | Catalogue Management | BR-8 | A book with an active issue cannot be deleted, and total copies cannot drop below the number currently issued.
AC-MEM-01 | Member Management | FR-2 | Librarian can register a member with name, contact details and membership type. New members are Active with a unique member code and unique email.
AC-MEM-02 | Member Management | FR-2 | Librarian can update contact details, membership type and status.
AC-MEM-03 | Member Management | BR-8 | A member with an active issue cannot be deleted.
AC-SRCH-01 | Search & Availability | FR-9 / BR-9 | Search matches partial, case-insensitive text across title, author, category and ISBN, for both librarian and students.
AC-SRCH-02 | Search & Availability | FR-7 | Every result shows correct availability.
AC-SRCH-03 | Search & Availability | BR-10 | An unavailable book shows the earliest expected return date.
AC-SRCH-04 | Search & Availability | FR-9 | No results, empty input and special characters are handled without errors.
AC-ISS-01 | Issue Book | FR-3 / BR-1 | A valid issue creates a transaction linked to the member and book, with due date = issue date + 14 days.
AC-ISS-02 | Issue Book | FR-7 / BR-5 | Issuing reduces available copies by exactly 1.
AC-ISS-03 | Issue Book | FR-8 / BR-3 / BR-4 | Issue is blocked, with the specific reason shown, if copies are 0, the member is not Active, the member has an unpaid fine, or the member already has 5 books.
AC-ISS-04 | Issue Book | BR-5 | A blocked or failed issue changes nothing in the database.
AC-ISS-05 | Issue Book | BR-5 | Two simultaneous issues of the last copy result in exactly one success.
AC-RET-01 | Return Book & Fines | FR-4 | Librarian records a return. Return date and transaction status (Returned) update automatically.
AC-RET-02 | Return Book & Fines | FR-5 / BR-2 | Returned on or before the due date means no fine. Returned late means fine = days late x Rs 5 with no cap, and status Unpaid.
AC-RET-03 | Return Book & Fines | FR-7 / BR-5 | Return increases available copies by 1 and never above total copies.
AC-RET-04 | Return Book & Fines | BR-6 | A transaction cannot be returned twice.
AC-FIN-01 | Fine Payment | FR-6 | Librarian can view fines and filter by Paid and Unpaid.
AC-FIN-02 | Fine Payment | BR-7 | Paying marks the fine Paid in full and records paid date and collector. No partial payments exist.
AC-FIN-03 | Fine Payment | BR-7 / BR-4 | A Paid fine cannot be paid again. Once a member's unpaid fines are cleared, issuing is allowed again.
AC-STU-01 | Student View | FR-10 | A student sees own current books with due dates (overdue highlighted), history, and fines with status.
AC-STU-02 | Student View | FR-10 | A student with nothing to show sees clear empty states.
AC-SLIP-01 | Slips & Printing | BR-12 | Issue, return and fine payment each produce an on-screen slip with correct details that can be printed or saved as PDF.
AC-OFF-01 | Offline Mode (PWA) | FR-9 | After one online visit, catalogue search works offline with a last-synced banner.
AC-OFF-02 | Offline Mode (PWA) | Design | All write actions are disabled offline with a clear message, and work again when back online.
AC-NFR-01 | Non-Functional | NFR-1 | Catalogue search and issuing complete in under 2 seconds.
AC-NFR-02 | Non-Functional | NFR-7 | The app works in Chrome, Firefox, Safari and Edge, and is usable at mobile widths.
AC-NFR-03 | Non-Functional | NFR-3 | A new librarian can learn the core tasks within 30 minutes.
AC-NFR-04 | Non-Functional | NFR-8 | SCHEMA.md and code comments document the system clearly.
AC-DATA-01 | Data Integrity & Dates | BR-5 | Database constraints stop negative stock, available above total, and duplicate ISBN, member code or email even if the frontend is bypassed.
AC-DATA-02 | Data Integrity & Dates | BR-11 | All dates use India time (Asia/Kolkata) and are compared as whole days.

## Test Cases
ID | Feature | Linked requirement | Type | Priority | Test case | Steps / input | Expected result | Actual result | Status | Tested by | Date | Notes
TC-AUTH-01 | Login & Access Control | FR-10 | Functional | High | Librarian logs in with valid credentials | Open login page. Enter the librarian email and password. Click Log In. | Librarian dashboard opens with all management menus. |  | Not run
TC-AUTH-02 | Login & Access Control | FR-10 | Negative | High | Login with wrong password | Enter a valid email and a wrong password. | Login rejected with a generic error. No dashboard access. |  | Not run
TC-AUTH-03 | Login & Access Control | FR-10 | Negative | Medium | Login with empty fields | Leave email and password blank and click Log In. | Validation message shown. No login attempt succeeds. |  | Not run
TC-AUTH-04 | Login & Access Control | FR-10 | Functional | High | Student logs in with valid credentials | Log in with a seeded student account. | Student view opens (search and My account only). No librarian menus. |  | Not run
TC-AUTH-05 | Login & Access Control | FR-10 | Security | High | Open a dashboard URL without logging in | Log out, then paste a dashboard or management URL in the browser. | Redirected to the login page. No data shown. |  | Not run
TC-AUTH-06 | Login & Access Control | NFR-2 | Security | High | Passwords are not stored as plain text | Check the auth users and database in the Supabase dashboard. | No readable passwords anywhere. Only hashes (handled by Supabase Auth). |  | Not run
TC-AUTH-07 | Login & Access Control | FR-10 | Functional | Medium | Student first-time sign-up with a registered email | Librarian registers a member email. Student signs up with that same email. | Account created and linked to the member record. Student sees only their own data. |  | Not run
TC-AUTH-08 | Login & Access Control | FR-10 | Security | High | Sign-up with an email the librarian has not registered | Try to sign up with an unregistered email. | No access to any data. Clear message shown. |  | Not run
TC-AUTH-09 | Login & Access Control | FR-10 / RLS | Security | High | Student opens librarian pages by URL | While logged in as a student, paste URLs of Issue, Return, Members, Fines pages. | Blocked or redirected. No librarian data shown. |  | Not run
TC-AUTH-10 | Login & Access Control | FR-10 / RLS | Security | High | Student calls a librarian action directly | As a student, call the issue/return/pay functions via the browser console or API tool. | Rejected by the database. No data changed. |  | Not run
TC-AUTH-11 | Login & Access Control | FR-10 / RLS | Security | High | Student tries to read another member's records | As a student, query transactions and fines of a different member through the API. | Only the student's own rows are returned. Others' rows are not visible. |  | Not run
TC-AUTH-12 | Login & Access Control | FR-10 | Functional | Medium | Logout ends the session | Log out, then press the browser Back button. | Protected pages do not show data. Login required again. |  | Not run
TC-AUTH-13 | Login & Access Control | Security | Security | High | Service role key is not in frontend code | Search the code and browser Sources/Network for service_role. | Not found. Only the public anon key is used. |  | Not run
TC-AUTH-14 | Login & Access Control | Security | Security | High | Row Level Security is enabled on every table | In Supabase, check each table: authors, categories, books, members, profiles, transactions, fines. | RLS is on for all tables, with policies defined. |  | Not run
TC-CAT-01 | Catalogue Management | FR-1 | Functional | High | Add a book with all valid fields | Fill title, ISBN, author, category, publisher, total copies = 3. Save. | Book appears in the list. Available copies = 3. |  | Not run
TC-CAT-02 | Catalogue Management | FR-1 | Negative | High | Add a book with a duplicate ISBN | Add a second book using an existing ISBN. | Rejected with a clear message. No duplicate created. |  | Not run
TC-CAT-03 | Catalogue Management | FR-1 | Negative | Medium | Add a book with missing or invalid fields | Leave title blank, or enter total copies = -1. | Validation errors shown. Nothing saved. |  | Not run
TC-CAT-04 | Catalogue Management | FR-1 | Functional | Medium | Edit a book | Change a book's title and publisher. Save. | Changes saved and shown in the list and search. |  | Not run
TC-CAT-05 | Catalogue Management | BR-8 | Edge | High | Reduce total copies below the number currently issued | Book has 2 copies issued. Set total copies to 1. | Rejected with a clear message. |  | Not run
TC-CAT-06 | Catalogue Management | BR-5 | Edge | Medium | Increase total copies | Increase total copies by 2. | Available copies also increases by 2. Available never exceeds total. |  | Not run
TC-CAT-07 | Catalogue Management | FR-1 | Functional | Medium | Delete a book with no transactions | Delete a newly added book. | Book removed from the list and search. |  | Not run
TC-CAT-08 | Catalogue Management | BR-8 | Edge | High | Delete a book that has an active issue | Try to delete a book currently issued to someone. | Blocked with a clear message. Book remains. |  | Not run
TC-CAT-09 | Catalogue Management | FR-1 | Functional | Medium | Add, edit and delete an author | Create an author, rename it, then delete one with no books. | Each action works and is reflected in the book forms. |  | Not run
TC-CAT-10 | Catalogue Management | FR-1 / BR-8 | Edge | Medium | Delete an author or category that has books | Try to delete an author or category linked to existing books. | Blocked or handled safely with a message. No orphan books. |  | Not run
TC-CAT-11 | Catalogue Management | FR-1 | Negative | Medium | Add a duplicate category name | Create a category with an existing name. | Rejected with a clear message. |  | Not run
TC-CAT-12 | Catalogue Management | FR-1 / RLS | Security | High | Student cannot modify the catalogue | As a student, try to add, edit or delete a book via UI and API. | Not possible in UI. API calls are rejected. |  | Not run
TC-MEM-01 | Member Management | FR-2 | Functional | High | Register a member with valid details | Enter name, email, phone, membership type. Register. | Member created as Active with a unique member code. |  | Not run
TC-MEM-02 | Member Management | FR-2 | Negative | Medium | Register with missing name or invalid email | Leave name blank, or enter an invalid email. | Validation message. Nothing saved. |  | Not run
TC-MEM-03 | Member Management | FR-2 | Negative | High | Register with a duplicate email | Use an email that already belongs to a member. | Rejected with a clear message. |  | Not run
TC-MEM-04 | Member Management | FR-2 | Functional | Medium | Update member contact and membership type | Edit phone and membership type. Save. | Changes saved and visible on the member profile. |  | Not run
TC-MEM-05 | Member Management | FR-2 / FR-8 | Functional | High | Set a member to Inactive | Change an Active member's status to Inactive. | Status updates. Issuing to this member is now blocked (see Issue tests). |  | Not run
TC-MEM-06 | Member Management | BR-8 | Edge | High | Delete a member with an active issue | Try to delete a member holding an issued book. | Blocked with a clear message. |  | Not run
TC-MEM-07 | Member Management | FR-2 | Functional | Low | Delete a member with no activity | Delete a newly created member. | Member removed. |  | Not run
TC-MEM-08 | Member Management | FR-2 / RLS | Security | High | Student cannot register or edit members | As a student, try to register or edit a member via UI and API. | Not possible. API calls are rejected. |  | Not run
TC-SRCH-01 | Search & Availability | FR-9 | Functional | High | Search by partial title | Search for the first few letters of a known title. | Matching books are listed. |  | Not run
TC-SRCH-02 | Search & Availability | FR-9 | Functional | High | Search by author name | Search for an author's name. | That author's books are listed. |  | Not run
TC-SRCH-03 | Search & Availability | FR-9 | Functional | Medium | Search by category | Search for a category name. | Books in that category are listed. |  | Not run
TC-SRCH-04 | Search & Availability | FR-9 | Functional | High | Search by full ISBN | Enter a complete ISBN. | The exact book is listed. |  | Not run
TC-SRCH-05 | Search & Availability | BR-9 | Functional | High | Search is case-insensitive | Search 'PYTHON' and then 'python'. | Both return identical results. |  | Not run
TC-SRCH-06 | Search & Availability | BR-9 | Functional | Medium | Search matches partial text inside words | Search 'prog' for a book titled 'Programming ...'. | Book is listed. |  | Not run
TC-SRCH-07 | Search & Availability | FR-9 | Edge | Medium | Search with no matches | Search a nonsense string. | Friendly 'No books found' message. No error. |  | Not run
TC-SRCH-08 | Search & Availability | FR-9 | Edge | Low | Search with empty input | Click Search with an empty box. | Full catalogue is shown (or a clear prompt). No error. |  | Not run
TC-SRCH-09 | Search & Availability | FR-9 | Security | Medium | Search with special characters | Search %, _, a single quote, and ' OR 1=1 --. | No error and no unintended results. |  | Not run
TC-SRCH-10 | Search & Availability | FR-7 | Functional | High | Availability matches real stock | Compare displayed availability with available_copies in the database for several books. | Status shown always matches the stored count. |  | Not run
TC-SRCH-11 | Search & Availability | BR-10 | Functional | High | Unavailable book shows earliest return date | Book has 0 copies and two active issues with different due dates. | Earliest due date is displayed. |  | Not run
TC-SRCH-12 | Search & Availability | FR-9 | Functional | Medium | Students can search too | Log in as a student and run a search. | Same results as the librarian sees, read-only. |  | Not run
TC-ISS-01 | Issue Book | FR-3 / BR-1 | Functional | High | Issue an available book to an eligible member | Book with copies > 0. Member Active, no fines, fewer than 5 books. Confirm Issue. | Transaction created and linked to the member. Status Issued. |  | Not run
TC-ISS-02 | Issue Book | BR-1 | Functional | High | Due date is issue date + 14 days | Issue a book and check the due date. | Due date = issue date + 14 days. |  | Not run
TC-ISS-03 | Issue Book | FR-7 / BR-5 | Functional | High | Stock decreases on issue | Note available copies, issue the book, check again. | Available copies reduced by exactly 1. |  | Not run
TC-ISS-04 | Issue Book | FR-8 / BR-4 | Negative | High | Block issue when 0 copies are available | Try to issue a book with 0 available copies. | Blocked with a 'no copies available' message. Nothing changes. |  | Not run
TC-ISS-05 | Issue Book | FR-8 / BR-4 | Negative | High | Block issue for an Inactive member | Try to issue to an Inactive member. | Blocked with a 'member not active' message. |  | Not run
TC-ISS-06 | Issue Book | BR-4 | Negative | High | Block issue for a member with an unpaid fine | Try to issue to a member with an Unpaid fine. | Blocked with an 'unpaid fine' message. |  | Not run
TC-ISS-07 | Issue Book | BR-3 / BR-4 | Negative | High | Block issue at the 5-book limit | Member already has 5 issued books. Try to issue a 6th. | Blocked with a 'limit reached' message. |  | Not run
TC-ISS-08 | Issue Book | BR-3 | Edge | High | Boundary: 4th to 5th book succeeds, 6th fails | Member has 4 books. Issue a 5th, then try a 6th. | 5th succeeds. 6th is blocked. |  | Not run
TC-ISS-09 | Issue Book | BR-4 | Functional | High | Issue allowed again after paying a fine | Pay the member's unpaid fine, then issue a book. | Issue succeeds. |  | Not run
TC-ISS-10 | Issue Book | BR-4 | Functional | Medium | Issue allowed again after returning a book at the limit | Member at 5 books returns one, then a new book is issued. | Issue succeeds. |  | Not run
TC-ISS-11 | Issue Book | FR-3 | Negative | Medium | Unknown Book ID or Member ID | Enter IDs that do not exist. | Clear error. Nothing created. |  | Not run
TC-ISS-12 | Issue Book | FR-3 | Negative | Medium | Blank fields on the issue form | Click Check Availability or Confirm Issue with empty fields. | Validation messages shown. |  | Not run
TC-ISS-13 | Issue Book | FR-8 | Functional | Medium | Check Availability button | Check a book with copies, then one with none. | Shows Available or Unavailable correctly. |  | Not run
TC-ISS-14 | Issue Book | BR-5 | Edge | High | Issue the last copy | Book has exactly 1 copy. Issue it, then try again. | First succeeds (available = 0). Second is blocked. |  | Not run
TC-ISS-15 | Issue Book | BR-5 | Edge | High | Concurrency: two librarians issue the last copy together | Open two sessions. Both try to issue the last copy at the same moment. | Exactly one succeeds. Available never goes negative. |  | Not run
TC-ISS-16 | Issue Book | BR-4 | Edge | Medium | Member blocked for several reasons at once | Use an Inactive member who also has an unpaid fine. | Blocked with a clear message (ideally listing all reasons). |  | Not run
TC-ISS-17 | Issue Book | BR-5 | Edge | High | A blocked issue changes nothing | After any blocked attempt, compare available copies and transaction count. | No new transaction and stock unchanged. |  | Not run
TC-ISS-18 | Issue Book | FR-3 / RLS | Security | High | Student cannot issue books | As a student, call the issue function through the API. | Rejected. No data changed. |  | Not run
TC-RET-01 | Return Book & Fines | FR-4 | Functional | High | Return a book before the due date | Return an issued book with the return date earlier than the due date. | Status Returned, return date set, no fine. |  | Not run
TC-RET-02 | Return Book & Fines | BR-2 | Edge | High | Return exactly on the due date | Return on the due date. | No fine (Rs 0). No fine record created. |  | Not run
TC-RET-03 | Return Book & Fines | BR-2 | Edge | High | Return 1 day late | Use a test transaction due yesterday and return it today. | Fine of Rs 5, days late = 1, status Unpaid. |  | Not run
TC-RET-04 | Return Book & Fines | BR-2 | Functional | High | Return 10 days late | Use a transaction 10 days overdue. | Fine of Rs 50. |  | Not run
TC-RET-05 | Return Book & Fines | BR-2 | Edge | Medium | Return 100 days late (no cap) | Use a transaction 100 days overdue. | Fine of Rs 500. |  | Not run
TC-RET-06 | Return Book & Fines | FR-7 / BR-5 | Functional | High | Stock increases on return | Note available copies, return a book, check again. | Available copies increased by exactly 1. |  | Not run
TC-RET-07 | Return Book & Fines | BR-5 | Edge | Medium | Available never exceeds total copies | After returns, compare available and total for the book. | Available is never greater than total. |  | Not run
TC-RET-08 | Return Book & Fines | BR-6 | Negative | High | Return an already returned transaction | Try to return the same transaction twice. | Rejected with a clear message. Stock not increased again. |  | Not run
TC-RET-09 | Return Book & Fines | BR-6 | Negative | Medium | Return a transaction that does not exist or is not issued | Enter a wrong or unissued ID. | Clear error. Nothing changes. |  | Not run
TC-RET-10 | Return Book & Fines | FR-5 | Functional | High | Fine record is linked correctly | After a late return, open the fine record. | Linked to the correct transaction and member. |  | Not run
TC-RET-11 | Return Book & Fines | FR-4 / RLS | Security | High | Student cannot record returns | As a student, call the return function through the API. | Rejected. No data changed. |  | Not run
TC-FIN-01 | Fine Payment | FR-6 | Functional | High | View unpaid fines | Open the Fines page. | Unpaid fines show member, book, days late and amount. |  | Not run
TC-FIN-02 | Fine Payment | BR-7 | Functional | High | Mark an unpaid fine as Paid | Click Mark as Paid on an Unpaid fine. | Status Paid, paid date set, collected by = librarian. |  | Not run
TC-FIN-03 | Fine Payment | BR-7 | Negative | High | Pay an already paid fine | Try to pay the same fine again. | Rejected or no change. No double payment recorded. |  | Not run
TC-FIN-04 | Fine Payment | BR-7 | Functional | Medium | No partial payment option | Look at the payment screen. | Only a full-amount payment is possible. |  | Not run
TC-FIN-05 | Fine Payment | FR-6 | Functional | Medium | Filter fines by Paid and Unpaid | Switch the filter between Paid and Unpaid. | Lists change correctly. |  | Not run
TC-FIN-06 | Fine Payment | BR-7 / RLS | Security | High | Student cannot mark fines Paid | As a student, call the pay function through the API. | Rejected. Fine unchanged. |  | Not run
TC-FIN-07 | Fine Payment | BR-4 | Functional | Medium | Paying clears the issue block | Pay the member's last unpaid fine, then check the Issue screen. | Member is no longer blocked for fines. |  | Not run
TC-STU-01 | Student View | FR-10 | Functional | High | Student sees own issued books | Log in as a student with active issues. | Current books with due dates are shown. |  | Not run
TC-STU-02 | Student View | FR-10 | Functional | Medium | Overdue books are highlighted | Use a student with an overdue book. | Overdue book clearly highlighted. |  | Not run
TC-STU-03 | Student View | FR-10 | Functional | High | Student sees own fines and status | Use a student with Paid and Unpaid fines. | Both fines shown with correct status. |  | Not run
TC-STU-04 | Student View | FR-10 | Functional | Medium | Student sees issue history | Use a student with returned books. | Past transactions listed with return dates. |  | Not run
TC-STU-05 | Student View | FR-10 | Edge | Low | Student with no activity | Log in as a student with no issues or fines. | Clear empty states. No errors. |  | Not run
TC-STU-06 | Student View | FR-10 | Functional | Medium | Student view updates after librarian actions | Librarian issues a book. Student refreshes. | New book appears on the student's list. |  | Not run
TC-SLIP-01 | Slips & Printing | BR-12 | Functional | Medium | Issue slip content | Issue a book and view the slip. | Shows member, book, issue date, due date and slip date. |  | Not run
TC-SLIP-02 | Slips & Printing | BR-12 | Functional | Medium | Return slip content | Return a late book and view the slip. | Shows return date and fine details where applicable. |  | Not run
TC-SLIP-03 | Slips & Printing | BR-12 | Functional | Medium | Fine payment slip content | Pay a fine and view the slip. | Shows member, amount, paid date. |  | Not run
TC-SLIP-04 | Slips & Printing | BR-12 | Functional | Medium | Print and Save as PDF | Click Print on a slip and choose Save as PDF. | Slip prints cleanly without menus or buttons. |  | Not run
TC-OFF-01 | Offline Mode (PWA) | FR-9 | Functional | Medium | Service worker registers on the deployed site | Open the deployed HTTPS site and check DevTools > Application. | Service worker active. Catalogue cached. |  | Not run
TC-OFF-02 | Offline Mode (PWA) | FR-9 | Functional | High | Catalogue search works offline | Visit online once, switch to airplane mode, search. | Search works using cached data. |  | Not run
TC-OFF-03 | Offline Mode (PWA) | FR-9 | Functional | Medium | Offline banner with last-synced time | Go offline and reload. | Banner shows 'Offline: data last synced at [time]'. |  | Not run
TC-OFF-04 | Offline Mode (PWA) | Design | Functional | High | Write actions are disabled offline | Offline, try issue, return, pay, add, edit, delete. | All disabled with a clear message. Nothing queued. |  | Not run
TC-OFF-05 | Offline Mode (PWA) | Design | Functional | Medium | Reconnect restores normal operation | Turn the connection back on. | Banner disappears, data refreshes, writes work again. |  | Not run
TC-OFF-06 | Offline Mode (PWA) | Design | Edge | Low | First visit while offline | Open the site offline on a device that never loaded it. | Friendly message. No crash. |  | Not run
TC-OFF-07 | Offline Mode (PWA) | Design | Edge | Low | Stale data is labelled | Another device issues a book. Check the offline device. | Old availability shown with the last-synced label. |  | Not run
TC-NFR-01 | Non-Functional | NFR-1 | Performance | High | Search under 2 seconds | Run 5 searches with seed data and time each (DevTools Network). | Every search completes in under 2 seconds. |  | Not run
TC-NFR-02 | Non-Functional | NFR-1 | Performance | High | Issue under 2 seconds | Time 5 issue operations. | Every issue completes in under 2 seconds. |  | Not run
TC-NFR-03 | Non-Functional | NFR-5 | Performance | Low | Capacity: 50,000 books and 10,000 members | Load dummy data with a script. Run searches and an issue. | No noticeable slowdown. Searches still under 2 seconds. |  | Not run
TC-NFR-04 | Non-Functional | NFR-7 | Compatibility | High | Full workflow in Chrome | Login, search, issue, return, pay fine. | All steps work. |  | Not run
TC-NFR-05 | Non-Functional | NFR-7 | Compatibility | Medium | Full workflow in Firefox | Repeat the workflow. | All steps work. |  | Not run
TC-NFR-06 | Non-Functional | NFR-7 | Compatibility | Medium | Full workflow in Safari | Repeat the workflow. | All steps work. |  | Not run
TC-NFR-07 | Non-Functional | NFR-7 | Compatibility | Medium | Full workflow in Edge | Repeat the workflow. | All steps work. |  | Not run
TC-NFR-08 | Non-Functional | NFR-7 | Compatibility | Medium | Usable at mobile width | Open key screens on a phone or at 375 px width. | No horizontal scrolling. Buttons and forms usable. |  | Not run
TC-NFR-09 | Non-Functional | NFR-3 | Usability | Medium | New user learns core tasks within 30 minutes | Give a classmate a 10-minute walkthrough, then ask them to issue and return a book. | Completes both without help. Note any confusion. |  | Not run
TC-NFR-10 | Non-Functional | NFR-8 | Maintainability | Medium | Documentation exists | Open SCHEMA.md and skim the code. | Every table, column and function described. Non-obvious logic commented. |  | Not run
TC-NFR-11 | Non-Functional | NFR-4 / NFR-6 | Documentation | Low | Backup and uptime documented | Check the report and hosting plan. | Daily backups and 99% uptime described as design targets, with plan limits noted. A manual export tested once. |  | Not run
TC-NFR-12 | Non-Functional | NFR-5 | Performance | Low | Indexes exist on search fields | Check the schema for indexes on title, isbn, member_code. | Indexes present. |  | Not run
TC-DATA-01 | Data Integrity & Dates | BR-5 | Security | High | Negative stock rejected by the database | Directly try to set available_copies = -1 via the API. | Rejected by a constraint. |  | Not run
TC-DATA-02 | Data Integrity & Dates | BR-5 | Security | High | Available above total rejected | Directly set available_copies greater than total_copies. | Rejected by a constraint. |  | Not run
TC-DATA-03 | Data Integrity & Dates | BR-5 | Security | High | Duplicate unique values rejected at database level | Directly insert a duplicate ISBN, member code or email. | Rejected by a unique constraint. |  | Not run
TC-DATA-04 | Data Integrity & Dates | BR-11 | Edge | High | Dates use India time | Issue a book between 00:00 and 05:30 IST, or review the function code. | Issue date matches the India date, not the previous day. |  | Not run
TC-DATA-05 | Data Integrity & Dates | BR-1 | Edge | Medium | Due date across month and year end | Issue a book on 25 December. | Due date is 8 January of the next year. |  | Not run
TC-DATA-06 | Data Integrity & Dates | BR-8 | Functional | Medium | Referential integrity | Try to delete a record that other rows depend on. | Blocked or handled safely. No orphan records. |  | Not run
TC-DATA-07 | Data Integrity & Dates | Seed | Functional | Medium | Seed script runs cleanly | Run the SQL seed on an empty database. | No errors. Data matches the brief (about 30 books, 10 members, overdue and fines). |  | Not run